## ProjectScope_Configuration
Phase | Item ID | Scope Item Description | Enabled (Yes/No) | Configuration/Details (Specify versions, platforms, tools, numbers, complexity etc.)
1. Planning & Strategy | 1.1 | Automation Strategy Definition | No | Goals, ROI analysis, scope boundaries, high-level approach
| 1.2 | Tooling Research & Proof of Concept (POC) | No | Consider: Separate tools (Web: Selenium/Cypress, Mobile: Espresso/XCUITest) vs. Cross-Platform (Appium)? Reporting? Test Mgmt Integration?
| 1.3 | Final Tool Selection & Licensing | No | Specify chosen tools & license costs (e.g., Cloud device farms)
| 1.4 | Define Target Platforms & Environments | No | Test Env URLs, API Endpoints, Mobile App Build locations
| 1.4.1 | Web: Target Browsers & Versions | No | e.g., Chrome latest, Firefox latest-1, Safari 15+. Consider: Responsive web testing across viewports?
| 1.4.2 | Mobile iOS: Target Devices, OS Versions, Types & Orientations | No | e.g., iPhone 13(iOS 16), iPad Pro(iOS 16); Specify: Screen sizes/types (Phone/Tablet), Orientations (Portrait/Landscape) to cover.
| 1.4.3 | Mobile Android: Target Devices, OS Versions, Types & Orientations | No | e.g., Pixel 6(And 13), Samsung Tablet(And 12); Specify: Screen sizes/types (Phone/Tablet), Orientations (Portrait/Landscape) to cover.
| 1.5 | Define Automation Scope (Test Case Identification) | No | Method (Risk-based, Regression coverage, etc.), Prioritization strategy.
| 1.6 | Test Data Strategy Definition | No | Approach (Static, Generated, API-driven, DB query). Consider: Cross-platform data needs?
2. Infrastructure & Setup | 2.1 | Source Code Repository Setup | No | e.g., Git (GitHub, GitLab), Branching strategy
| 2.2 | Infrastructure: Test Environment Provisioning | No | VM Setup, Server config, Network access
| 2.3 | Infrastructure: Web Driver / Browser Setup | No | Local setup, Selenium Grid, Cloud Grid (Sauce Labs, BrowserStack)
| 2.4 | Infrastructure: Mobile Simulators / Emulators Setup | No | Local setup (Xcode Simulators, Android SDK Emulators), versions required.
| 2.5 | Infrastructure: Real Mobile Device Lab Setup / Configuration | No | Local devices (USB Hubs), Cloud Device Farm (Sauce Labs, BrowserStack). Specify: Device connection/management method.
| 2.6 | CI/CD: Pipeline Setup / Configuration | No | Tool (e.g., Jenkins, GitLab CI, GitHub Actions). Consider: Complexity of managing multi-platform pipelines.
| 2.7 | CI/CD: Basic Build & Compile Pipeline Stage | No | Checks out code, resolves dependencies (Web/iOS/Android), compiles framework.
| 2.8 | CI/CD: Agent/Runner Configuration for Platforms | No | Setup machines/containers for Web (Browsers), iOS (macOS, Xcode), Android (SDK).
3. Framework Development | 3.1 | Core Framework Architecture Design | No | Consider: Adaptability for Web, iOS, Android specific needs.
| 3.2 | Project Structure Setup | No | Folders, Modules, Naming conventions.
| 3.3 | Base Test Classes / Test Runner Integration | No | e.g., TestNG, JUnit, Pytest integration.
| 3.4 | Driver Management (Web/Mobile) | No | Initializing/closing drivers, session handling. Consider: Appium server management if used.
| 3.5 | Platform Abstraction Layer (Crucial for Cross-Platform) | No | Code to handle differences between Web, iOS, Android interactions smoothly.
| 3.6 | UI Mapping Implementation (e.g., Page/Screen Object Model) | No | Strategy for locating elements. Consider: Complexity of stable cross-platform locators (Web DOM vs Native Accessibility IDs/XPath etc.)
| 3.7 | Common Utilities Development | No | Waits, Assertions, Data readers, API clients, Screenshots. Consider: Platform-specific utils needed?
| 3.8 | Configuration Management Implementation | No | Handling Env URLs, credentials, timeouts per platform.
| 3.9 | Test Data Management Implementation | No | Implement chosen strategy (Item 1.6).
| 3.1 | Logging Implementation | No | Framework logs, Test step logs.
| 3.11 | Initial Reporting Integration | No | Connect framework output to basic reporting (e.g., Allure, Extent).
4. Test Case Scripting | 4.1 | Detailed Test Case Design for Automation | No | Specify Source: Are tests being (A) Converted from existing manual cases OR (B) Created New based on requirements/features? Estimate Mix: (e.g., 70% Conversion, 30% New). Design includes defining steps, data, expected results suitable for automation. Note: Creating new tests requires more initial analysis effort.
| 4.2 | Scripting - Web: Develop Automated Tests | No | Number/Complexity. Factor in Source (4.1): Effort per test varies if converting vs. creating new. Consider responsive elements (1.4.1).
| 4.3 | Scripting - Mobile iOS: Develop Automated Tests | No | Number/Complexity. Factor in Source (4.1): Effort per test varies. Consider layout (1.4.2), native features, gestures.
| 4.4 | Scripting - Mobile Android: Develop Automated Tests | No | Number/Complexity. Factor in Source (4.1): Effort per test varies. Consider layout (1.4.3), native features, gestures.
| 4.5 | Scripting - API Tests (if supporting UI) | No | Number/Complexity. Factor in Source (4.1): Effort per test varies if converting existing API tests vs. creating new ones.
| 4.6 | Test Data Preparation / Generation Scripts | No | Creating specific data needed for scripted tests.
| 4.7 | Implement Cross-Browser / Cross-Device / Cross-OS Compatibility | No | Handling variations in locators/behavior across targets (Items 1.4.x). Effort can be high.
| 4.8 | Code Reviews for Automation Scripts | No | Process, frequency.
| 4.9 | Integration with Test Management Tool (Optional) | No | e.g., Pushing results to TestRail, Zephyr.
5. Execution & Reporting | 5.1 | CI/CD: Automated Test Execution Pipeline Stage(s) | No | Triggering (manual, scheduled, on commit), Parallel execution strategy?
| 5.1.1 | CI/CD: Execution Orchestration | No | Managing conditional/dependent execution across platforms.
| 5.2 | CI/CD: Execution on Web Platforms | No | Pipeline jobs for browsers defined in 1.4.1.
| 5.3 | CI/CD: Execution on iOS Platforms | No | Pipeline jobs for devices/OS defined in 1.4.2.
| 5.3.1 | CI/CD: iOS App Deployment/Installation | No | Mechanism to get the .ipa file onto simulators/devices.
| 5.4 | CI/CD: Execution on Android Platforms | No | Pipeline jobs for devices/OS defined in 1.4.3.
| 5.4.1 | CI/CD: Android App Deployment/Installation | No | Mechanism to get the .apk/.aab file onto emulators/devices.
| 5.5 | Advanced Reporting Setup / Dashboard Configuration | No | Customizing reports, aggregating multi-platform results, creating dashboards.
| 5.6 | Notification System Setup | No | Alerts on failures (e.g., Slack, Email). Consider: Platform-specific alerts?
| 5.7 | Results Analysis & Triage Process Definition | No | Who analyzes failures (needs multi-platform skills?), how are defects logged?
6. Maintenance & Handover | 6.1 | Documentation (Framework, Setup, Usage, Troubleshooting) | No | Level of detail. Consider: Documenting platform-specific nuances.
| 6.2 | Team Training / Handover Session | No | Cover Web, iOS, Android specifics.
| 6.3 | Ongoing: Test Script Maintenance Plan | No | Budgeted effort (e.g., X hours/sprint). Consider: Higher effort due to application changes on 3 platforms.
| 6.4 | Ongoing: Framework Maintenance & Enhancement Plan | No | Budgeted effort for updates, dependency mgmt (OS, browser, library updates).
| 6.5 | Ongoing: Infrastructure / Environment Maintenance | No | Keeping OS, Browsers, Devices, Xcode, Android SDK, CI/CD tools updated.
7. Project Management | 7.1 | Project Planning & Coordination | No | Meetings, Status reporting, Risk management (higher complexity here).
| 7.2 | Stakeholder Communication | No | Demos, Feedback sessions.

## Detail Estimation
Phase | Item ID | Scope Item Description | Enabled | Configuration/Details (Revised Scenario w/ Complexity) | Est. Effort (MD) | Notes/Assumptions
1. Planning & Strategy | 1.1 | Automation Strategy Definition | Yes | Goals, ROI, Scope boundaries defined | 2 | Essential kickoff activity
| 1.2 | Tooling Research & Proof of Concept (POC) | Yes | POC focuses on Appium for Web/iOS/Android feasibility, Allure reporting | 5 | Confirms core toolchain viability
| 1.3 | Final Tool Selection & Licensing | Yes | Appium, Jenkins, Allure (free), Cloud Device Farm (costs budgeted separately) | 1 | Final decisions and vendor interaction if needed
| 1.4 | Define Target Platforms & Environments | Yes | Test Env URLs, Build locations documented | 1
| 1.4.1 | Web: Target Browsers & Versions | Yes | Chrome latest, Firefox latest | 0.5 | Included in 1.4
| 1.4.2 | Mobile iOS: Target Devices, OS, Types & Orientations | Yes | iPhone 14(iOS 17), iPhone 13(iOS 16), Phone only, Portrait/Landscape | 0.5 | Included in 1.4
| 1.4.3 | Mobile Android: Target Devices, OS, Types & Orientations | Yes | Pixel 7(And 14), Samsung S22(And 13), Phone only, Portrait/Landscape | 0.5 | Included in 1.4
| 1.5 | Define Automation Scope (Test Case Identification) | Yes | Identify ~100 key tests (mix of regression, key features) | 3 | Crucial for defining scripting scope
| 1.6 | Test Data Strategy Definition | Yes | API-driven data setup preferred, fallback to static data | 1 | High-level strategy
Phase 1 Subtotal |  |  |  |  | 13
2. Infrastructure & Setup | 2.1 | Source Code Repository Setup | Yes | GitHub repo, Gitflow branching strategy | 0.5 | Standard setup
| 2.2 | Infrastructure: Test Environment Provisioning | Yes | Coordination with Ops/DevOps for stable test env access | 2 | Assumes env mostly exists, needs config/access
| 2.3 | Infrastructure: Web Driver / Browser Setup | Yes | Configure execution via Cloud Grid (e.g., Sauce Labs/BrowserStack) | 2 | Integration with cloud provider
| 2.4 | Infrastructure: Mobile Simulators / Emulators Setup | Yes | Local setup on CI agents/dev machines for basic checks | 1 | Primarily for framework dev/debugging
| 2.5 | Infrastructure: Real Mobile Device Lab Setup / Configuration | Yes | Configure execution via Cloud Device Farm (e.g., Sauce Labs/BrowserStack) | 2 | Integration with cloud provider
| 2.6 | CI/CD: Pipeline Setup / Configuration | Yes | Jenkins pipeline definition. Assumed: Standard Complexity | 6 | (Revised based on Standard Complexity table)
| 2.7 | CI/CD: Basic Build & Compile Pipeline Stage | Yes | Checkout, dependency resolution (Maven/Gradle/NPM), compile framework | 2 | Validates basic framework integrity
| 2.8 | CI/CD: Agent/Runner Configuration for Platforms | Yes | Configure Jenkins agents (Docker?) with necessary tools (Node, Java, Appium) | 3 | Setup execution environments
Phase 2 Subtotal |  |  |  |  | 18
3. Framework Development | 3.1-3.11 | All Framework Items (Core Arch, Abstraction, Utils, Reporting...) | Yes | Build robust, multi-platform framework. Assumed: Standard Abstraction (3.5) | 40 | (Estimate covers all Phase 3 items; reflects effort for Standard Platform Abstraction Layer)
Phase 3 Subtotal |  |  |  |  | 40
4. Test Case Scripting | 4.1 | Test Case Design for Automation (Source Definition) | Yes | 60% Convert (~60 TCs), 40% New (~40 TCs). | 16 | (Estimate based on TC Complexity table inputs)
| 4.2 | Scripting - Web: Develop Automated Tests | Yes | ~50 TCs total (breakdown per complexity table) | 24 | (Estimate based on TC Complexity table calculation)
| 4.3 | Scripting - Mobile iOS: Develop Automated Tests | Yes | ~50 TCs total (breakdown per complexity table) | 30 | (Estimate based on TC Complexity table calculation)
| 4.4 | Scripting - Mobile Android: Develop Automated Tests | Yes | ~50 TCs total (breakdown per complexity table) | 30 | (Estimate based on TC Complexity table calculation)
| 4.5 | Scripting - API Tests (if supporting UI) | No | N/A | 0 | Out of scope for this example
| 4.6 | Test Data Preparation / Generation Scripts | Yes | Scripts/utilities to support test data needs based on 1.6 | 5 | (Effort highly dependent on specific data needs)
| 4.7 | Implement Cross-Browser / Cross-Device / Cross-OS Compatibility | Yes | Debugging/tweaking across target matrix | 10 | (Effort depends heavily on application consistency)
| 4.8 | Code Reviews for Automation Scripts | Yes | Peer reviews integrated into workflow | 10 | (Revised ~10% of updated raw scripting effort 4.2-4.4)
| 4.9 | Integration with Test Management Tool (Optional) | No | N/A | 0 | Out of scope for this example
Phase 4 Subtotal |  |  |  |  | 125
5. Execution & Reporting | 5.1 | CI/CD: Automated Test Execution Pipeline Stage(s) | Yes | Trigger manually / nightly build | 3 | Defining execution stages in Jenkinsfile
| 5.1.1 | CI/CD: Execution Orchestration | Yes | Assumed: Standard Parallel Complexity | 3 | (Revised based on Standard Parallel Complexity table)
| 5.2 | CI/CD: Execution on Web Platforms | Yes | Jenkins stage to run Web tests on Cloud Grid | 1 | Configuration for web execution
| 5.3 | CI/CD: Execution on iOS Platforms | Yes | Jenkins stage to run iOS tests on Cloud Device Farm | 2 | Configuration for iOS execution
| 5.3.1 | CI/CD: iOS App Deployment/Installation | Yes | Scripting app upload/install to Cloud Farm devices | 1 | Necessary step for mobile
| 5.4 | CI/CD: Execution on Android Platforms | Yes | Jenkins stage to run Android tests on Cloud Device Farm | 2 | Configuration for Android execution
| 5.4.1 | CI/CD: Android App Deployment/Installation | Yes | Scripting app upload/install to Cloud Farm devices | 1 | Necessary step for mobile
| 5.5 | Advanced Reporting Setup / Dashboard Configuration | Yes | Allure report generation/serving. Assumed: Standard Enhanced | 4 | (Revised based on Standard Enhanced Complexity table)
| 5.6 | Notification System Setup | Yes | Slack notifications on pipeline failure | 1 | Standard CI feature configuration
| 5.7 | Results Analysis & Triage Process Definition | Yes | Document process for reviewing failures | 1 | Defining workflow, not execution time
Phase 5 Subtotal |  |  |  |  | 19
6. Maintenance & Handover | 6.1 | Documentation (Framework, Setup, Usage, Troubleshooting) | Yes | Assumed: Standard Complexity | 6 | (Revised based on Standard Complexity table)
| 6.2 | Team Training / Handover Session | Yes | Knowledge transfer session | 2
| 6.3 | Ongoing: Test Script Maintenance Plan | Yes | Budgeted Separately | (Ongoing) | e.g., Estimate ~15-20% of initial scripting effort per year
| 6.4 | Ongoing: Framework Maintenance & Enhancement Plan | Yes | Budgeted Separately | (Ongoing) | e.g., Estimate ~10-15% of initial framework effort per year
| 6.5 | Ongoing: Infrastructure / Environment Maintenance | No | N/A | 0 | Assumed handled outside this project's scope
Phase 6 Subtotal (Initial) |  |  |  |  | 8 | Effort for initial build only (6.1 + 6.2)
7. Project Management | 7.1 | Project Planning & Coordination | Yes | Meetings, Status reporting, Risk management | 32 | (Revised ~15% of updated technical effort Ph 2-5 + 6.1, 6.2)
| 7.2 | Stakeholder Communication | Yes | Demos, Feedback sessions |  | Included in 7.1
Phase 7 Subtotal |  |  |  |  | 32
TOTAL INITIAL EFFORT (Sum of Subtotals) |  |  |  |  | 255 | Sum of Phases 1-5 + 6 (Initial) + 7
Contingency (Risk Buffer) |  |  |  | Example: 20% of Total Initial Effort | 51 | Example: 20% of 258 PD
GRAND TOTAL ESTIMATED EFFORT (Initial Build) |  |  |  |  | 306 | Total Initial Effort + Contingency
Ongoing Maintenance Effort |  |  |  |  | ~20-35 MD/Quarter | Separate Budget: Estimate based on % of initial effort or dedicated time

## 4. Categorize Test Cases
Complexity Level | Definition / Characteristics Summary | Example Effort Range (PD/TC) - WEB | Example Effort Range (PD/TC) - MOBILE (iOS/Android) | Example # of TCs (Your Project) | Est. Effort WEB (MD) | Est. Effort MOBILE (MD)
Low | < 7 steps, linear flow, simple interactions & validation, static data, stable elements. | 0.1 - 0.3 | 0.15 - 0.4 | e.g., 20 Web, 20 Mobile | (20 * ~0.2) = 4 | (20 * ~0.25) = 5
Medium | 7-15 steps, some navigation, standard interactions, multiple validations, simple data setup/waits. | 0.3 - 0.7 | 0.4 - 0.9 | e.g., 20 Web, 20 Mobile | (20 * ~0.5) = 10 | (20 * ~0.6) = 12
High | >15 steps, complex E2E flow, complex interactions/validation/data/waits, native features (mobile). | 0.7 - 1.5+ | 0.9 - 2.0+ | e.g., 10 Web, 10 Mobile | (10 * ~1.0) = 10 | (10 * ~1.3) = 13
Totals |  |  |  | e.g., 50 Web, 50 Mobile | 24 | 30

## 2.6 CICD Pipeline Setup
Complexity Level | Definition / Characteristics Summary | Example Effort Range (MD) | Selected Level (Your Project) | Estimated Effort (MD)
Basic | Single pipeline, manual trigger, simple build/test stages, fixed agent config, basic source control integration. | 2 to 4
Standard | Multiple triggers (commit, schedule), separate stages, basic env handling, standard agent config, integrates source control & basic notifications. | 4 to 8 | Selected | 6
Complex | Dynamic triggers/branching, parallel stages, dynamic env provisioning, matrix builds, advanced agent config (containers, scaling), significant scripting, integrates multiple external tools. | 8 to 15+

## 3.5 Platform Abstraction Layer
Complexity Level | Definition / Characteristics Summary | Example Effort Range (MD) | Selected Level (Your Project) | Estimated Effort (MD)
Minimal | Simple conditional logic within tests/page objects for major differences. Relies heavily on generic selectors/methods or separate native tool implementations. | 2 to 4
Standard | Dedicated layer wrapping common actions (click, type). Handles common divergences (locators, basic APIs) using standard patterns (Adapter). Suitable for Appium. | 4 to 10 | Selected | 8
Extensive | Deep abstraction for significant UI/API differences. Custom wrappers? Handles complex platform specifics transparently. Needed for very divergent apps. | 10 to 20+

## 5.1.1 CICD Execution Orchestr
Complexity Level | Definition / Characteristics Summary | Example Effort Range (MD) | Selected Level (Your Project) | Estimated Effort (MD)
Basic Sequential | Runs suites/platforms one after another. Simple pass/fail logic. | 1 to 2
Standard Parallel | Runs suites/platforms concurrently on different agents. Static test/agent allocation. Basic retries maybe. | 2 to 5 | Selected | 3
Advanced Dynamic | Sophisticated parallelism (sharding), dynamic agent allocation, smart test selection/ordering (fail fast), complex retries, conditional stage execution. | 5 to 10+

## 5.5 Advanced Reporting Setup
Complexity Level | Definition / Characteristics Summary | Example Effort Range (MD) | Selected Level (Your Project) | Estimated Effort (MD)
Basic Integrated | Standard report from chosen tool (e.g., Allure, Extent) published as CI artifact. | 1 to 2
Standard Enhanced | Customized tool report (metadata, attachments), results aggregation, basic dashboard within CI tool. | 3 to 6 | Selected | 4
Advanced Custom | Custom dashboards (Grafana?), data pushed to external DB/Test Mgmt Tool, trend analysis, advanced metrics/filtering, integration with defect tracking, custom visualizations. | 6 to 12+

## 6.1 Documentation
Complexity Level | Definition / Characteristics Summary | Example Effort Range (MD) | Selected Level (Your Project) | Estimated Effort (MD)
Basic | README (setup, basic usage), core component overview. | 2 to 4
Standard | Basic + How-to guides, code comments, maybe generated API docs, architectural overview. | 4 to 8 | Selected | 6
Comprehensive | Standard + Detailed diagrams, troubleshooting guide, contribution guidelines, full API docs, usage examples, explanation of design choices. | 8 to 15+